## Sheet1
DEVELOPERS.
Ubong Udoette
Matthew LAY
James Karanja
Saad Nahian
WEEK | TASK | DESCRIPTION | DEADLINE | PRINCIPAL DEVELOPER | SECOND DEVELOPER | REVIEWERS
1 | Project Management | Setting up individual repository account | 14/04/2024. | James Karanja |  | All team members
|  | Kanban management planning for each week | 14/04/2024. | James Karanja |  | All team members
| Task 2: Test First Development | test plans provided by each member | 14/04/2024. | All members |  | All team members
All team members
2 | Task 3.1 : Initial setup | Develop the back end supplier classes. and setup | 21/04/2024 | Ubong Udoette | Mathew Lay | All team members
| Task 3.2: producing the CARE system | Provide functionality for the CARE interface | 21/04/2024 | Ubong Udoette | Mathew Lay | All team members
| Task 3.3: Design | Provide design functionality for the CARE interface | 21/04/2024 | Ubong Udoette | Mathew Lay | All team members
All team members
3 | Task 3.4: Testing | Testing the software with Junit | 25/04/2024 | Saad Nahian | Ubong Udoette & Matthew Lay | All team members
| Task 3.5: Persistence | Saving game to file and loading from file. | 25/04/2024 | Mathew Lay | Ubong Udoette & Matthew Lay | All team members
| Task 3.6 Graphical User Interface. | Producing the Graphical Interface | 25/04/2024 | Saad Nahian |  | All team members
| Technical Report/Documentation |  | 25/04/2024 | James Karanja | Mathew Lay | All team members